## Sheet1
Process Model | Pros | Cons | Execution of Project
Waterfall | As with Waterfall in general, we will get fully defined requirements ahead of development, helping to ensure less churn and scope creep. | Way too long between project Planning and Analysis, and having something actually developed. In a project this big, it would be 10 years Even though requirements may be "fully" defined before development, a project that takes this long is going to have changes made to early assumptions. Things like environment, financial, and community need. | Planners should organize requirements and analysis such that the early infrastructure and commonalities be defined first. That would allow further analsys of other parts of the system to be done in parallel; meaning multiple pars of the analysis can be done simultaneusly, there by reducing that step of the Waterfall method.
Parallel Development | Allows quicker time to market. If done correctly, each of the items under Project Scope could be done somewhat in parallell. | Probably too much inner decpendencies between the various parts of the project to do them simultaneously and gain the benefits of true paralell development . | Clearly analyze and define the dependencies as best as possible. Though there will be churn during actual development, it can be minimized. Once this is done, that start a parallel development between project scope components. Proceeding with caution, and ensuring that the project teams are highly managed and coordinated to identify impacting dependencies as early as possible.
RAD Phased | This particular project was actually defined in such a manner that a phased approach is most beneficial. By developing in phases the risk of churn and rework is minimized | There is a risk, although minimized, earlier phases need to be re-worked as later phases are more well defined. | Define phase progression like you would build a house. Provide a solid foundation, a well-defined supporting structure and roof, build the rooms, finish the interior, etc. In doing it that way, each phase builds on the previous with little or no churn. Have you every seen a well-built house where the foundation was changed after the roof was put on? Given the project scope, determine the order of the phases, taking into account all inner depedencies. That way, each phase can commence with risk minimized.
Agile | Allows for early development and demonstration of the most important parts of the system. If multiple scrum teams are defined, work can go on both incrementally and in parallell across scrum teams. That is to say, multiple scope items can be developed in parallell. | This is a very large system, agile works better for smaller projects. While Agile methods can work for almost any project size and scope, the disadvantage becomes not necessarily with the actual Agile method, but with coordination of scrum teams to ensure that are incrementally building integratable pieces that will not need to change later. | There are a number of ways in which this can be broken down. I would start with the infrastructure pieces of the project, and run them through Agile development. Then, as it becomes more apparent that more work can be done across project scope items, add scrum teams to begin developing the various pieces incrementally and in parallell. Release demonstrations would be done along the way to first show that the infrastructure develpment is progressing, the as other work begins, demonstrate how the various scope items are built on top of the infrastructure to add capabilities.